REPORT OF COORDINATOR

term 1 2015/2016

| school name | Liceo Scientifico «G. Galilei» Napoli - ITALY |
| --- | --- |
| coordinator | Ciro De Rosa |

| number of teachers involved in project | 15 |
| --- | --- |
| number of students involved in project | 25 |

| Is it the first Erasmus+ school education project at your school? | YES |
| --- | --- |
| Is your headmaster/deputy headmaster involved in project, participates in any meetings? | YES |
| Is there Erasmus + corner at school? | YES |
| Is project web site promoted on school web site? | YES |
| Are parents, local society, school board informed about the project? | YES |

MEETINGS with STUDENTS at school

(type of meeting: indroduction, lecture, lab, posters preparation, any other activity

| nr | type of lesson | number of students | Topic Time (in hours) |
| --- | --- | --- | --- |
| 1 | Introduction | 25 | Intruducing the project to students and parents 2 hrs |
| 2 | Science | 25 | Entry Test + work program for 1st year |
| 3 | Science | 25 | Volcanoes |
| 4 | Science | 25 | Volcanoes |

EXCURSION

| nr | number of teachers | number of students | Short description ( till 5 sentences) Time (in hours) |
| --- | --- | --- | --- |
| 1 | 1 | 20 | Mineralogy Museum 3hrs |
| 2 | 1 + Guide | 20 | Volcano Solfatara 3 hrs |

VOLCANO MODEL

| number of students involved | Short description ( till 5 sentences) |
| --- | --- |
| How was the activity promoted at school? .NOT HELD YET . THE SCHOOL HAD TO WAIT FOR NA FUNDING WHICH WAS DELAYED |  |

TEACHER COMPETITION  FOR THE BEST LESSON PLAN

| Have you announced the competition so far? | NO |
| --- | --- |
| Have you prepared rules of the competition so far? | YES |
| Have you prepared poster informing about the competition so far? | NO |
| If you announced the competition, where was it promoted? |  |

What kinds of materials have you send so far to project web site?

| Materials | Sent | Number |
| --- | --- | --- |
| Videos | YES | 1 |
| Photos | YES | 10 |
| Posters | NO |  |
| Articles | YES | 3 Reports |

TRANSNATIONAL MEETING ( filled by host teacher)

| Number of teachers from school involved | 2 |
| --- | --- |
| Total number of teachers participating | 12 |
| Date of the meeting | 22/11-26/11 |
| Type of activities during the meeting | Teacher meetimng to plan, Scientific excursions, Cultural visits |

Other:

| Have you worked out system of project budget control at school so far? | YES |
| --- | --- |
| Does school managment/ headmaster help you in the project? | YES |

| Have you sent impressions after last meeting? | YES |
| --- | --- |
| Have you filled LINKS (tab in web site) and sent to coordinator? | YES |
| Have you sent results of basic knowledge test about volcanos, earthquakes, earth - in % | YES |

What else have you done so far which is not mentioned in the report form?

Planning and scheduling activities for April 2016 students and teachers exchange;

Listing stduents and matching hosta nd guests.

Presenting project at Open House Day

Launched Official Logo Competition

24 students tested

38 %  weak knowledge     54%  basic   8% good /advanced